## Read Me
Compliance Hub — Refined PostgreSQL Design
Decision baseline: hybrid typed columns + configurable data points; two-week illustrative fee demo using seeded data; versioned product/packaging records with locked snapshots.
Topic | Decision / Guidance
Purpose | A practical starting design for the two-week prototype and a scalable path toward the MVP. This is a proposed schema, not a regulator-approved data model.
Core rule | Collect data once → validate → review → lock a data-round snapshot → let Compliance, Fee Calculation and DPP read the same snapshot.
Hybrid data strategy | Use typed columns for stable entities and high-value fields (SKU, GTIN, weight, units, dates, currency). Use configurable data-point definitions and value records for variable country/regulation fields.
Where JSONB fits | Use JSONB for flexible payloads from imports, raw source rows, mapping suggestions and non-core calculation metadata. Do not use one giant JSONB object as the main product database.
Versioning | Keep stable product/component identities separate from versioned product and packaging data. A data round locks references to the versions that were reviewed.
Two-week fee scope | Seeded sample tariff/rule data and clearly labelled illustrative estimates. No claim of production-accurate fees, live regulatory updates, live Devex/Snowflake integration or real submission.
Source grounding | The uploaded page-priority map marks P1 as two-week demo scope, P2 as MVP, and P3 as later. The mockup shows 23 screens across setup, data collection, compliance, fees and DPP.
Implementation order | 1) Core schema + seed data; 2) Product and packaging flow; 3) configurable data points and collection; 4) validation and snapshots; 5) illustrative fee and DPP views; 6) demo QA.
Important caveat | Confirm the exact DP01–DP45 field names, units, source systems and market applicability against the team's Excel before treating the mapping sheet as final. Fields not explicit in the source should not be silently assumed.

## Proposed Schema
Proposed PostgreSQL Tables
Suggested table inventory. PK = primary key; FK = foreign key. UUID IDs are recommended; use timestamptz for audit timestamps.
Table | Purpose | Suggested fields (not exhaustive) | Design note | Related screen(s)
organisations | Client / company workspace | id UUID PK; name TEXT; legal_name TEXT; organisation_size_id UUID FK; home_country_code CHAR(2); reporting_currency CHAR(3); status TEXT; created_at TIMESTAMPTZ | Stable client identity. Avoid storing every subsidiary as a separate client workspace unless access boundaries require it. | Setup: Onboarding; Dashboard
legal_entities | Subsidiaries / legal entities | id UUID PK; organisation_id UUID FK; name TEXT; registration_number TEXT; country_code CHAR(2); rpd_organisation_id TEXT NULL; status TEXT | One organisation can have many legal entities; includes UK RPD organisation ID where applicable. | Onboarding; Producer Check
users | People using the tool | id UUID PK; organisation_id UUID FK; email CITEXT UNIQUE; display_name TEXT; role_id UUID FK; status TEXT; created_at TIMESTAMPTZ | For prototype, auth may be mocked; do not store plaintext passwords. Use an auth provider later. | Sign In; roles/permissions
roles | Configurable access roles | id UUID PK; code TEXT UNIQUE; name TEXT; permissions JSONB | Seed Admin, Client User, Reviewer, Approver. Permissions JSONB is acceptable for evolving UI permissions. | Sign In; approval
markets | Country / subnational markets | id UUID PK; code TEXT UNIQUE; name TEXT; parent_market_id UUID FK NULL; currency_code CHAR(3); active BOOLEAN | Examples UK, FR, DE, California. A parent market can group submarkets. | Onboarding; market workspaces
sectors | Industry categories | id UUID PK; code TEXT UNIQUE; name TEXT; active BOOLEAN | Seed Food & Beverage, Batteries, Cosmetics, Electronics etc. | Onboarding; template builder
organisation_sectors | Organisation-to-sector link | organisation_id UUID FK; sector_id UUID FK; PRIMARY KEY (organisation_id, sector_id) | Many-to-many relationship. | Onboarding
organisation_markets | Markets enabled for an organisation | organisation_id UUID FK; market_id UUID FK; enabled_from DATE; enabled_to DATE NULL; PRIMARY KEY (organisation_id, market_id, enabled_from) | Tracks which markets are in scope; avoid hardcoding market checkboxes in application code. | Onboarding; dashboard
regulations | Regulation / scheme catalogue | id UUID PK; code TEXT UNIQUE; name TEXT; market_id UUID FK; regulation_type TEXT; active BOOLEAN | Catalogue only; rule logic and effective dates live in versioned rule tables. | Onboarding; Compliance
regulation_versions | Versioned regulation/rule set | id UUID PK; regulation_id UUID FK; version_label TEXT; effective_from DATE; effective_to DATE NULL; status TEXT; rule_config JSONB; created_at TIMESTAMPTZ | JSONB is suitable for rule configuration, but calculation logic must be validated and versioned. Seed demo versions only. | Apply Rules; fee trace
products | Stable product/SKU identity | id UUID PK; organisation_id UUID FK; sku_code TEXT; gtin TEXT NULL; product_name TEXT; brand TEXT NULL; sector_id UUID FK NULL; status TEXT; created_at TIMESTAMPTZ | Keep identity stable; enforce unique SKU per organisation. GTIN may be nullable if not supplied. | Product list; product detail
product_versions | Versioned product attributes | id UUID PK; product_id UUID FK; version_no INT; pack_size_value NUMERIC NULL; pack_size_unit TEXT NULL; product_category TEXT NULL; valid_from DATE; valid_to DATE NULL; source_system_id UUID FK NULL; source_record_ref TEXT NULL; created_at TIMESTAMPTZ; UNIQUE(product_id, version_no) | Changes create a new version rather than overwriting a previously approved product state. | Product detail; snapshot
packaging_components | Stable packaging component identity | id UUID PK; product_id UUID FK; component_code TEXT NULL; component_name TEXT; packaging_level_id UUID FK NULL; parent_component_id UUID FK NULL; status TEXT | Represents bottle, cap, label, pouch, carton, etc. Parent link can model packaging tree; consider a separate BOM table if components are reused across SKUs. | Packaging tree
component_versions | Versioned packaging attributes | id UUID PK; component_id UUID FK; version_no INT; material_id UUID FK NULL; polymer_type_id UUID FK NULL; weight_g NUMERIC(12,4) NULL; recycled_content_pct NUMERIC(5,2) NULL; colour TEXT NULL; reusable BOOLEAN NULL; multi_material BOOLEAN NULL; valid_from DATE; valid_to DATE NULL; source_system_id UUID FK NULL; source_record_ref TEXT NULL; created_at TIMESTAMPTZ; UNIQUE(component_id, version_no) | Weight and composition changes create a new version. Use numeric units consistently; keep original imported value/unit in import records. | Product detail; validation; fees; DPP
materials | Material catalogue | id UUID PK; code TEXT UNIQUE; name TEXT; material_group TEXT NULL; active BOOLEAN | Seed common materials; support regulated material classifications through mappings rather than material-name strings everywhere. | Packaging tree; rules
polymer_types | Polymer catalogue | id UUID PK; code TEXT UNIQUE; name TEXT; active BOOLEAN | Keep separate from broad materials because the source data points distinguish main material and polymer type. | Packaging tree
packaging_levels | Packaging-level catalogue | id UUID PK; code TEXT UNIQUE; name TEXT; active BOOLEAN | Primary, secondary, tertiary etc.; labels can vary by regulatory context via mappings. | Product detail; UK EPR
suppliers | Supplier identity | id UUID PK; organisation_id UUID FK; name TEXT; country_code CHAR(2) NULL; email CITEXT NULL; status TEXT | Supplier is linked to the client workspace. Supplier portal access should be scoped to assigned requests/components. | Supplier portal; requests
component_suppliers | Component-to-supplier relationship | component_id UUID FK; supplier_id UUID FK; valid_from DATE; valid_to DATE NULL; is_primary BOOLEAN; PRIMARY KEY(component_id, supplier_id, valid_from) | A component can have multiple suppliers over time; don't put a single supplier name directly on component identity. | Product detail; request data
source_systems | Source system catalogue | id UUID PK; organisation_id UUID FK; code TEXT; name TEXT; system_type TEXT; status TEXT | Seed Trace One Devex, Snowflake, Manual/Client and Supplier. Actual connectors can come later. | Onboarding; data quality
data_point_definitions | Configurable field catalogue | id UUID PK; code TEXT UNIQUE; label TEXT; description TEXT NULL; data_type TEXT; unit_code TEXT NULL; entity_type TEXT; is_core BOOLEAN; is_cost_driving BOOLEAN; is_required_default BOOLEAN; validation_config JSONB; options_config JSONB; active BOOLEAN | Central configuration for DP01–DP45 and future fields. Validate data_type against an allowed list in application/database constraints. | Template builder; dynamic forms
data_point_applicability | Where a data point applies | id UUID PK; data_point_id UUID FK; market_id UUID FK NULL; regulation_id UUID FK NULL; sector_id UUID FK NULL; required_override BOOLEAN NULL; effective_from DATE NULL; effective_to DATE NULL | A field can apply globally or only to a market/regulation/sector. Add constraints to prevent duplicate overlapping configurations. | Template builder; compliance; DPP
data_point_values | Values for configurable fields | id UUID PK; data_point_id UUID FK; entity_type TEXT; entity_id UUID; value_text TEXT NULL; value_number NUMERIC NULL; value_boolean BOOLEAN NULL; value_date DATE NULL; value_json JSONB NULL; unit_code TEXT NULL; source_system_id UUID FK NULL; source_ref TEXT NULL; confidence NUMERIC(5,2) NULL; verification_status TEXT; recorded_at TIMESTAMPTZ | Typed value columns allow filtering/validation. Enforce one matching value column for the definition's data_type; entity_id is polymorphic so validate target in app or use entity-specific value tables if strict FK integrity is required. | Dynamic forms; imports; validation
data_rounds | Collection/review round | id UUID PK; organisation_id UUID FK; round_code TEXT; reporting_period_start DATE; reporting_period_end DATE; status TEXT; started_by UUID FK; locked_at TIMESTAMPTZ NULL; created_at TIMESTAMPTZ | Statuses: draft, collecting, reviewing, approved, locked. A locked round must be immutable. | Data collection; confirmation
snapshot_product_versions | Product versions included in snapshot | snapshot_id UUID FK; product_version_id UUID FK; PRIMARY KEY(snapshot_id, product_version_id) | Create snapshot header table as data_snapshots; this table pins exact product versions used by downstream modules. | Data confirmation
data_snapshots | Immutable approved data snapshot | id UUID PK; data_round_id UUID FK UNIQUE; organisation_id UUID FK; snapshot_code TEXT; status TEXT; approved_by UUID FK NULL; approved_at TIMESTAMPTZ NULL; created_at TIMESTAMPTZ | Lock after approval. Store membership rows for product/component versions and relevant data point values; don't rely only on a live query. | Data confirmation; all downstream modules
snapshot_component_versions | Component versions included in snapshot | snapshot_id UUID FK; component_version_id UUID FK; PRIMARY KEY(snapshot_id, component_version_id) | Pins exact component attributes used for a reproducible calculation. | Snapshot; fees; DPP
snapshot_data_point_values | Configurable values included in snapshot | snapshot_id UUID FK; data_point_value_id UUID FK; PRIMARY KEY(snapshot_id, data_point_value_id) | Pins values selected for a snapshot; alternatively copy immutable value rows into snapshot tables if source values may be edited. | Snapshot; validation; compliance
evidence_documents | Evidence file metadata | id UUID PK; organisation_id UUID FK; supplier_id UUID FK NULL; file_name TEXT; storage_key TEXT; mime_type TEXT; document_type TEXT; uploaded_at TIMESTAMPTZ; uploaded_by UUID FK NULL; valid_from DATE NULL; expires_on DATE NULL; verification_status TEXT | Store file in object storage; PostgreSQL stores metadata and a private storage key, not the binary file itself. | Supplier portal; validation; DPP
evidence_links | Evidence-to-record links | id UUID PK; evidence_document_id UUID FK; entity_type TEXT; entity_id UUID; data_point_value_id UUID FK NULL; relation_type TEXT | Allows one certificate to support a component, value or product. Polymorphic entity links need application-level integrity checks. | Validation; audit pack
data_requests | Request sent to supplier/client | id UUID PK; data_round_id UUID FK; supplier_id UUID FK NULL; recipient_email CITEXT; status TEXT; due_at TIMESTAMPTZ NULL; sent_at TIMESTAMPTZ NULL; token_hash TEXT NULL; created_by UUID FK | Group multiple requested fields/components under one request/contact. Store only hashed magic-link tokens; implement expiry/one-time use. | Request Data; supplier portal
data_request_items | Requested fields/components | id UUID PK; data_request_id UUID FK; data_point_id UUID FK; entity_type TEXT; entity_id UUID; status TEXT; answered_at TIMESTAMPTZ NULL | Tracks field-level completion and supplier responses. | Request Data; supplier portal
validation_rules | Configurable validation checks | id UUID PK; code TEXT UNIQUE; name TEXT; scope_entity_type TEXT; rule_type TEXT; config JSONB; severity TEXT; active BOOLEAN | Examples required, numeric range, unit, sum-of-parts, sales-vs-shipment. Rule engine is configurable; first demo can implement a small known set. | Validation
validation_runs | Validation execution history | id UUID PK; data_round_id UUID FK; snapshot_id UUID FK NULL; run_at TIMESTAMPTZ; triggered_by TEXT; status TEXT | Each sync or manual run creates a record. | Validation; data quality
validation_issues | Validation findings | id UUID PK; validation_run_id UUID FK; rule_id UUID FK NULL; entity_type TEXT; entity_id UUID; data_point_id UUID FK NULL; severity TEXT; issue_code TEXT; message TEXT; estimated_impact_amount NUMERIC NULL; currency_code CHAR(3) NULL; status TEXT; assigned_to UUID FK NULL; resolved_at TIMESTAMPTZ NULL | Keep issue lifecycle separate from raw values. Estimated € impact is illustrative in demo and must be labelled accordingly. | Data quality; validation; dashboard
correction_requests | Requested change back to source | id UUID PK; data_round_id UUID FK; source_system_id UUID FK; entity_type TEXT; entity_id UUID; field_code TEXT; source_value JSONB; proposed_value JSONB; evidence_document_id UUID FK NULL; status TEXT; requested_by UUID FK; approved_by UUID FK NULL; sent_at TIMESTAMPTZ NULL; resolved_at TIMESTAMPTZ NULL | For demo, model queue and statuses only. Do not overwrite source system data or claim live write-back. | Corrections to Source
approval_events | Review/sign-off audit trail | id UUID PK; data_round_id UUID FK; action TEXT; actor_user_id UUID FK; comment TEXT NULL; created_at TIMESTAMPTZ | Append-only events: submitted, reviewed, approved, rejected, locked. | Validation; data confirmation
fee_tariffs | Seeded fee tariff catalogue | id UUID PK; regulation_version_id UUID FK; market_id UUID FK; material_id UUID FK NULL; fee_basis TEXT; rate NUMERIC(14,6); currency_code CHAR(3); effective_from DATE; effective_to DATE NULL; source_note TEXT | Seed illustrative values for demo and mark them as sample/illustrative. Keep tariff version visible in the trace. | Fee calculation
fee_calculation_runs | Fee calculation run header | id UUID PK; snapshot_id UUID FK; scenario_id UUID FK NULL; calculation_version TEXT; status TEXT; reporting_currency CHAR(3); fx_rate_date DATE NULL; created_at TIMESTAMPTZ; created_by UUID FK | Every run references a locked snapshot and a calculation version. | Dashboard; fee trace
fee_calculation_lines | Detailed calculation output | id UUID PK; calculation_run_id UUID FK; product_version_id UUID FK NULL; component_version_id UUID FK NULL; market_id UUID FK; tariff_id UUID FK NULL; units NUMERIC; weight_g NUMERIC; tonnage NUMERIC; base_fee NUMERIC; modulation_factor NUMERIC; total_fee NUMERIC; currency_code CHAR(3); explanation JSONB | Store line-level math and inputs so a fee can be traced. For the prototype, seed data and simple deterministic calculation only. | Fee trace; cost hotspots
scenarios | Saved what-if scenario | id UUID PK; organisation_id UUID FK; snapshot_id UUID FK; name TEXT; description TEXT NULL; assumptions JSONB; status TEXT; created_by UUID FK; created_at TIMESTAMPTZ | P2/P3 beyond initial demo unless time remains. Scenario must point to the baseline snapshot. | Scenario planner
dpp_product_groups | Products requiring passport | id UUID PK; organisation_id UUID FK; name TEXT; regulation_id UUID FK; granularity TEXT; obligation_start_date DATE NULL; status TEXT | DPP applicability is configurable by regulation and product group. | DPP product groups
dpp_passports | Passport record/version | id UUID PK; product_id UUID FK; product_version_id UUID FK; snapshot_id UUID FK; regulation_id UUID FK; version_no INT; status TEXT; public_identifier TEXT NULL; published_at TIMESTAMPTZ NULL; created_at TIMESTAMPTZ; UNIQUE(product_id, regulation_id, version_no) | For demo, generate preview/draft only. Actual registry publishing is out of scope. | DPP editor/public preview
dpp_field_definitions | Passport field configuration | id UUID PK; regulation_id UUID FK; code TEXT; label TEXT; data_type TEXT; required BOOLEAN; default_visibility TEXT; active BOOLEAN; UNIQUE(regulation_id, code) | Defines fields required by each passport type and default audience visibility. | DPP editor
dpp_field_values | Passport values and source references | id UUID PK; passport_id UUID FK; field_definition_id UUID FK; value_json JSONB; source_type TEXT; source_record_ref TEXT NULL; visibility TEXT; evidence_document_id UUID FK NULL; verification_status TEXT | Autofill from approved snapshot; preserve field-level source and visibility. | DPP editor
audit_events | General audit log | id UUID PK; organisation_id UUID FK; actor_user_id UUID FK NULL; entity_type TEXT; entity_id UUID; action TEXT; before_json JSONB NULL; after_json JSONB NULL; created_at TIMESTAMPTZ | Append-only for meaningful edits, approvals, lock/unlock and publication events. Avoid sensitive data in logs. | All screens
import_batches | Uploaded data/import run | id UUID PK; organisation_id UUID FK; source_system_id UUID FK NULL; file_name TEXT; storage_key TEXT; status TEXT; uploaded_by UUID FK; uploaded_at TIMESTAMPTZ; mapping_config JSONB NULL | Store source file metadata and mapping. Keep raw rows in import_rows or private object storage. | Upload + AI column mapping
import_rows | Raw uploaded row and mapping result | id UUID PK; import_batch_id UUID FK; row_number INT; raw_payload JSONB; mapped_payload JSONB NULL; mapping_confidence NUMERIC(5,2) NULL; processing_status TEXT; errors JSONB NULL | Preserve original input for troubleshooting; confirm mappings before writing canonical records. | Upload mapping; data quality

## Configurable Data Points
Configurable Data Point Model
A definition table describes each field; applicability controls where it is required; value rows hold typed values and provenance. Confirm exact DP names against the team's source workbook.
Case | Table / field | How it works | Implementation rule | Screen / note
DP01–DP45 | data_point_definitions | One row per field with stable code, label, type, unit, entity type, required/cost-driving flags, validation/options config. | Use the original DP code as immutable business key, e.g. DP01; do not rely on row number. | Definition seed must be verified against source Excel.
Market/regulation-specific fields | data_point_applicability | Link a field to a market, regulation and/or sector; optional overrides for requiredness and effective dates. | NULL market/regulation can mean global applicability, but define this convention consistently. | Use for UK-only fields such as RPD IDs/RAM-specific data.
Field values | data_point_values | Store value in a typed value column, plus unit, source system/reference, confidence and verification status. | Enforce exactly one value slot matching the definition type; app validation can enforce initially. | Keep original raw import separately.
Imported values | import_batches + import_rows | Store file metadata, raw row JSONB, mapped row JSONB, mapping confidence and errors. | Raw payload is for ingestion/audit, not the canonical source of truth. | Screen 8 upload + mapping.
Evidence | evidence_documents + evidence_links | File metadata, expiry, verification status and links to components/data-point values. | Use private object storage; store only key/metadata in PostgreSQL. | Supplier portal, validation, DPP.
Snapshot inclusion | snapshot_data_point_values | Pin exactly which field-value records were approved for a data round. | For stronger immutability, copy selected value payload/provenance into snapshot-owned rows at lock time. | Data confirmation feeds Modules 2–4.
Suggested allowed data types | data_point_definitions.data_type | text, integer, decimal, boolean, date, enum, multi_enum, json, file_reference | Store stable/core numeric values in typed columns on core tables where frequently queried; use generic value table for flexible points. | No need to make every field a physical SQL column.
Suggested validation_config JSONB | data_point_definitions.validation_config | Examples: min, max, precision, allowed_units, regex, required_if, sum_group, evidence_required. | Configuration describes validation; backend code implements supported rule types. | Keep config schema documented and versioned.
Suggested options_config JSONB | data_point_definitions.options_config | Enum options or UI metadata for fields where applicable. | For shared/global controlled vocabularies used in joins/reporting, prefer reference tables instead. | Template builder and dynamic forms.
Critical integrity note | data_point_values.entity_type/entity_id | A generic polymorphic reference does not get a normal PostgreSQL FK to multiple tables. | Prototype: validate target in service layer. If strict referential integrity is required, create separate product_data_point_values and component_data_point_values tables. | Decide before production.

## Relationships
Key Relationships & Snapshot Flow
Logical relationships for ERD planning. Add FK constraints, indexes and uniqueness constraints in migrations.
Relationship | Cardinality | Why it matters
Organisation → legal entities | organisations 1:N legal_entities | One client may have several legal entities/subsidiaries.
Organisation → products | organisations 1:N products | SKU uniqueness should be scoped to organisation.
Product → product versions | products 1:N product_versions | Each meaningful change creates a new version.
Product → packaging components | products 1:N packaging_components | A component can be nested via parent_component_id; for reusable BOMs, introduce product_component_links.
Component → component versions | packaging_components 1:N component_versions | Material, weight, recycled content and other versioned packaging attributes.
Component ↔ suppliers | packaging_components N:M suppliers via component_suppliers | Supports alternate suppliers and supplier changes over time.
Data point definition → applicability | data_point_definitions 1:N data_point_applicability | Defines market/regulation/sector-specific use.
Data point definition → values | data_point_definitions 1:N data_point_values | Values carry source, unit, confidence and verification status.
Data round → snapshot | data_rounds 1:0..1 data_snapshots | Only an approved round can be locked into a snapshot.
Snapshot → product/component versions | data_snapshots N:M versions via snapshot_*_versions | Pins exact records used by downstream calculations.
Snapshot → data point values | data_snapshots N:M values via snapshot_data_point_values | Prevents downstream screens from reading changing live values.
Snapshot → fee run | data_snapshots 1:N fee_calculation_runs | Every fee run references an immutable snapshot and calculation version.
Fee run → fee lines | fee_calculation_runs 1:N fee_calculation_lines | Line-level math makes cost trace reproducible.
Snapshot → DPP passport | data_snapshots 1:N dpp_passports | Passport is filled from a known approved data snapshot.
Data request → request items | data_requests 1:N data_request_items | A single supplier request can ask for multiple fields/components.
Validation run → issues | validation_runs 1:N validation_issues | Issue status is tracked separately from the source value.
Evidence document → evidence links | evidence_documents 1:N evidence_links | One file can support multiple fields/components.

## 2 Week Screen Plan
Two-Week Screen-wise Development Plan
Assumption: 10 working days, frontend/backend/database can work in parallel. P1 happy path only; external integrations and production regulatory engines are out of scope.
Day | Screen / Feature | Workstream | Development task | Acceptance criteria | Priority | Owner / team
1 | Foundation + Sign In / app shell | DB | Create migrations for organisations, legal_entities, users, roles, markets, sectors; seed demo tenant and users. | Tables migrate cleanly; seed script repeatable; no plaintext password storage. | P1 | Backend + DB
1 | Foundation + Sign In / app shell | Frontend/API | Sign-in mock flow, protected-route placeholder, shared layout/sidebar and route skeleton for 23-screen navigation. | Demo user can enter app; screen navigation works; auth is clearly mocked. | P1 | Frontend
2 | Onboarding wizard | DB/API | CRUD for legal entities, sectors, markets and selected regulations; seed market/regulation catalogue. | Selected markets and sectors persist for demo organisation. | P1 | Backend + Frontend
3 | Home Dashboard | DB/API | Seed dashboard aggregates: illustrative cost by market, confidence/uncertainty, data completeness, next deadline and sync/gap status. | Dashboard values come from seeded fixtures/query layer and are labelled illustrative. | P1 | Backend + Frontend
4 | Product list + product detail/packaging tree | DB | Create products, product_versions, packaging_components, component_versions, materials, polymer_types, packaging_levels, suppliers, component_suppliers. | Can create/view a SKU and multiple components with material, weight, supplier and version number. | P1 | Backend + DB
4 | Product list + product detail/packaging tree | Frontend/API | Product search/list, filters, detail view, packaging tree and version history indicator. | Create and edit demo product/component; old version remains retrievable after change. | P1 | Frontend + Backend
5 | Template builder + data collection | DB/API | Create data_point_definitions, data_point_applicability, data_point_values; seed verified DP01–DP45 definitions; build form metadata API. | Dynamic field list can be assembled from selected sector/format/market; no hardcoding every field in UI. | P1 | Backend + DB
5 | Template builder + data collection | Frontend | Template builder preview and initial data collection form using field metadata. | Fields render by type and show required/cost-driving/source labels where configured. | P1 | Frontend
6 | Upload + column mapping / Request Data | DB/API | Create import_batches/import_rows, data_requests/data_request_items; implement CSV/XLSX demo upload or fixture-based mapping preview. | User can inspect raw/mapped values and confirm a mapping; requests can be created and tracked. | P1 | Backend + Frontend
7 | Supplier portal + evidence | DB/API | Create evidence_documents/evidence_links; supplier request token flow for demo; response saves draft values; secure token design documented. | Supplier sees only assigned request items; can submit values and upload evidence metadata. | P1 | Backend + Frontend
7 | Validation + data quality | DB/API | Create validation_rules, validation_runs, validation_issues; implement required/range/unit and simple mismatch checks. | Validation run produces visible issues with severity, entity, field and status. | P1 | Backend + Frontend
8 | Corrections to source | DB/API | Create correction_requests and audit events; queue proposed vs verified values; mocked approval statuses only. | Can approve/reject a correction request; source system is not overwritten; demo labels write-back as mocked. | P1 | Backend + Frontend
8 | Data confirmation / lock snapshot | DB | Create data_rounds, data_snapshots, snapshot_product_versions, snapshot_component_versions, snapshot_data_point_values, approval_events. | Lock operation pins exact versions/values; locked round cannot be edited through normal API. | P1 | Backend + DB
8 | Data confirmation / lock snapshot | Frontend/API | Completeness summary, review status, approve-and-lock interaction and snapshot code display. | All downstream modules receive snapshot_id; changes require a new round/snapshot. | P1 | Frontend + Backend
9 | Producer determination + report preview | DB/API | Seed regulation versions and producer-determination examples; generate simple UK RPD/PPWR DoC preview from snapshot-backed seeded data. | Rules/results show rule version and plain-language reason; no real regulatory submission. | P1 | Backend + Frontend
9 | Illustrative fee calculation + trace | DB/API | Create fee_tariffs, fee_calculation_runs, fee_calculation_lines; seed illustrative tariff and FX inputs; calculate simple sample lines from snapshot. | Each number has source snapshot, calculation version, tariff version, inputs and formula trace; clearly marked illustrative. | P1 | Backend + Frontend
10 | DPP editor/public preview | DB/API | Create dpp_product_groups, dpp_passports, dpp_field_definitions, dpp_field_values; autofill from snapshot and render preview/QR placeholder. | Draft passport shows source per field and missing required fields; publishing/registry is mocked or omitted. | P1 | Backend + Frontend
10 | End-to-end demo QA | QA | Test onboarding → product → component → supplier data → validation → correction → lock snapshot → fee trace → DPP preview. | One seeded demo path works end-to-end; defects, out-of-scope items and known limitations documented. | P1 | Whole team

## Planner Tasks
Planner-ready Development Tasks
Copy individual rows into Planner. Keep task titles action-oriented; estimates are indicative and should be adjusted to team capacity.
Task ID | Task title | Bucket | Target day | Priority | Description | Definition of done
DB-01 | Define PostgreSQL schema and naming conventions | Database | Day 1 | P1 | Create initial ERD, UUID PK convention, timestamps, status enums/check constraints, FK/index standards. | ERD reviewed by backend + product owner.
DB-02 | Create organisation and onboarding migrations | Backend/DB | Day 1–2 | P1 | Build organisations, legal_entities, users, roles, markets, sectors, organisation_sectors, organisation_markets, regulations. | Migrations and seed data run cleanly.
DB-03 | Create product and packaging versioned tables | Backend/DB | Day 4 | P1 | Build products, product_versions, packaging_components, component_versions and reference catalogues. | A SKU can have multiple components and immutable versions.
DB-04 | Seed configurable DP01–DP45 definitions | Backend/Data | Day 5 | P1 | Map source Excel fields to stable codes, data types, units, entity types, sources, requiredness and market applicability. | Every mapped DP is traceable to the source workbook; unclear fields flagged for confirmation.
DB-05 | Implement data point value service | Backend | Day 5 | P1 | Read/write typed values, source provenance, confidence and verification status; validate type matches definition. | Dynamic field values persist and invalid types are rejected.
DB-06 | Implement import batch and mapping preview | Backend | Day 6 | P1 | Store uploaded file metadata, raw rows, mapped rows, confidence and errors; require user confirmation before canonical write. | Original rows remain available; mapping is reviewable.
DB-07 | Implement supplier request and evidence tables | Backend | Day 7 | P1 | Build data_requests, request_items, evidence metadata/links; enforce request scoping. | Supplier sees only assigned items and can submit evidence.
DB-08 | Implement validation rules and issue queue | Backend | Day 7 | P1 | Implement required, range, unit and simple source mismatch checks; persist validation runs/issues. | Issues show severity, field, record, status and owner.
DB-09 | Implement correction queue and audit trail | Backend | Day 8 | P1 | Store source value vs proposed value, evidence, approval and status; no real source write-back in demo. | Approval/rejection is audited and source data is not silently overwritten.
DB-10 | Implement immutable snapshot lock | Backend/DB | Day 8 | P1 | On approval, pin exact product/component versions and data point values; prevent normal edits to locked round. | Snapshot ID can reproduce the exact data used by fees/DPP.
DB-11 | Implement seeded illustrative fee engine | Backend | Day 9 | P1 | Seed sample tariff/rule versions and calculation inputs; persist calculation run and line-level math. | Fee trace shows inputs, formula, currency, tariff version and illustrative disclaimer.
DB-12 | Implement DPP draft from approved snapshot | Backend | Day 10 | P1 | Configure passport fields; autofill values with source and visibility; support draft/preview status. | Passport preview uses snapshot values and flags missing fields.
UI-01 | Build sign-in and shared navigation shell | Frontend | Day 1 | P1 | Mock sign-in, route guards placeholder, sidebar and screen navigation. | All demo routes are navigable.
UI-02 | Build onboarding wizard | Frontend | Day 2 | P1 | Company/legal entities, sectors, markets, laws and source-system mock status. | Selections save and can be revisited.
UI-03 | Build home dashboard with seeded KPIs | Frontend | Day 3 | P1 | Market cost table, uncertainty, completeness, deadline, sync/gap tiles. | UI labels illustrative/sample values clearly.
UI-04 | Build product list and packaging tree | Frontend | Day 4 | P1 | Search/filter product list, product detail, component tree and version history. | CRUD demo path works with API.
UI-05 | Build template builder and dynamic field renderer | Frontend | Day 5 | P1 | Render fields from data-point metadata; show units, source and required/cost-driving labels. | New configured field appears without UI code changes.
UI-06 | Build upload mapping and request queue | Frontend | Day 6 | P1 | Mapping preview/confirmation and supplier request status list. | User can confirm mapping and create a request.
UI-07 | Build supplier portal and evidence upload UI | Frontend | Day 7 | P1 | Token-based demo access, only assigned questions, draft/submit and evidence metadata. | Supplier submission updates request state.
UI-08 | Build validation and correction screens | Frontend | Day 7–8 | P1 | Issues list, source vs verified value, evidence, approve/reject actions. | Issue and correction statuses update.
UI-09 | Build data confirmation and lock screen | Frontend | Day 8 | P1 | Completeness by law, reviewer/approver status, snapshot ID and lock button. | Lock action returns snapshot ID and disables editing for that round.
UI-10 | Build compliance and fee trace screens | Frontend | Day 9 | P1 | Producer matrix, sample report preview, fee calculation trace and cost hotspot teaser. | Every output is labelled seeded/illustrative and linked to snapshot.
UI-11 | Build DPP editor and preview | Frontend | Day 10 | P1 | Passport field list, source, visibility, missing-field warnings, QR placeholder. | Draft preview is generated from locked snapshot.
QA-01 | Run end-to-end demo acceptance test | QA | Day 10 | P1 | Test one organisation, two products, components, supplier response, validation, correction, snapshot, fee and DPP. | Happy path and known limitations documented.
ARCH-01 | Document post-demo backlog and integration boundaries | Tech lead | Day 10 | P2 | List real SSO, live Devex/Snowflake connectors, robust rules engine, external submissions, registry publishing and production security as future scope. | P2/P3 backlog reviewed and prioritised.

## Decisions & Risks
Design Decisions, Risks & Out-of-scope
Use this as a review checklist before schema migrations and sprint commitments.
Status | Decision / risk | Rule | Why / action
Confirmed | Hybrid data model | Stable high-use fields use typed columns; flexible fields use definitions + typed value rows. | Avoids one giant JSONB blob and avoids schema migration for every new regulatory field.
Confirmed | Illustrative fee demo | Use seeded tariff/rule data and clearly mark outputs as illustrative. | Do not present as legal/regulatory calculation validation.
Confirmed | Versioned product/packaging data | Keep identity tables separate from product_versions/component_versions. | Preserves history and supports repeatable snapshots.
Confirmed | Locked snapshots | Modules 2, 3 and 4 read from approved snapshot_id. | Snapshot should pin exact versions and values; lock should be enforced in service layer and DB controls where feasible.
Recommended | Use UUID primary keys | Generate IDs in application or PostgreSQL; expose stable codes separately. | Avoids coupling relationships to SKU or DP labels.
Recommended | Use NUMERIC for measurements/money | Avoid float for weight, percentages and money; define units explicitly. | Prevents rounding/precision surprises.
Recommended | Use status CHECK constraints or lookup tables | Start with CHECK constraints for small stable lists; use lookup tables where client-configurable. | Do not use unconstrained free-text status everywhere.
Risk | Polymorphic entity_id has no FK | data_point_values/evidence_links with entity_type + entity_id need service validation or entity-specific link tables. | Choose based on desired referential-integrity strictness before production.
Risk | Source data conflicts | Do not silently overwrite source values; preserve source/proposed/verified values and provenance. | Correction write-back is mocked in two-week demo.
Risk | Tariffs/rules can change | Store effective dates and version IDs; every fee run must reference versions used. | Seed demo values only; regulatory owner must validate before production.
Out of scope for two-week demo | Live SSO, Devex/Snowflake connectors, AI extraction, real source write-back, actual regulatory submission, live registry publishing, production FX/tariffs. | Mock or fixture-backed flows only; document limitations on screen and in demo. | Prioritise P1 happy path.
Before implementation | Verify all DP01–DP45 source names, units, source systems, requiredness and market applicability against source Excel. | Do not infer missing definitions. Mark unresolved mappings as 'Needs confirmation'. | Avoids encoding incorrect assumptions into the schema.