## Dashboard
MONKSPACES ¦ PRODUCT DELIVERY DASHBOARD
Editable project plan • baseline starts 26-Oct-2026 • adjust dates, owners, status and % complete in the Tasks sheet. Timeline/Gantt updates from task dates.
Project start date | 2026-10-26 | Milestone | Target | Exit criteria
Planned horizon (weeks) | 8 | M1: Scope & data contract | 2026-11-06 | MVP scope, sample data and API contracts agreed
Total tasks |  | M2: First end-to-end slice | 2026-11-13 | CSV → validation → DB → API → Angular UI
Completed tasks |  | M3: Quality workflow | 2026-11-27 | Issue → correction → approval → revalidation + audit
In progress |  | M4: EPR engine | 2026-12-11 | One jurisdiction; reference cases reconcile
Blocked |  | M5: Demo / pilot decision | 2026-12-18 | Regression, security checks, demo and go/no-go
Overall completion
How to use this workbook |  | Planning note
1) Update task dates/owners/status/% complete in Tasks. 2) Review Gantt. 3) Track incoming client files in Data & Integrations. 4) Log defects and evidence in Testing. 5) Review open decisions every week. |  | This is a planning baseline, not a delivery commitment. Eight weeks targets a focused EPR proof-of-value only; live integrations depend on client API access, documentation, permissions and data quality.

## Tasks
TASK REGISTER
Edit start/end dates, owner, status and % complete. Gantt and dashboard are driven by this sheet. Use dates as Excel dates.
Task ID | Workstream | Phase | Task / Deliverable | Acceptance Criteria / Definition of Done | Owner Role | Start Date | End Date | Status | % Complete | Dependency / Client Input | Priority | Effort (person-days) | Notes / Risks
T001 | Architecture & Product | Day 0 | Confirm MVP scope and first EPR jurisdiction | Scope, exclusions, target jurisdiction and demo outcome documented | Solution Architect / Product Owner | 2026-10-26 | 2026-10-27 | Not Started | 0% | Client decision on jurisdiction | Critical | 2 | Do not implement jurisdiction-specific fee logic before rules are confirmed.
T002 | Client Data & Integrations | Day 0 | Request sample datasets and data dictionary | Sample product, packaging, sales-by-market files and field definitions received or request tracked | Solution Architect / Client IT | 2026-10-26 | 2026-10-28 | Not Started | 0% | Client data owner identified | Critical | 2 | Anonymized sample data is sufficient to start.
T003 | Client Data & Integrations | Day 0 | Request ERP/PLM/Snowflake API documentation and sandbox access | API docs, auth method, rate limits, test credentials/access process and owner identified | Integration Engineer / Client IT | 2026-10-26 | 2026-11-06 | Not Started | 0% | Client IT and source-system vendors | High | 4 | If access is delayed, continue using CSV and mock API responses.
T004 | Architecture & Product | Week 1 | Define architecture, environments and API contracts | Approved logical architecture, module boundaries, OpenAPI draft and dev/test environment plan | Solution Architect / Backend Lead | 2026-10-26 | 2026-11-02 | Not Started | 0% | T001 | Critical | 4 | Start as a modular monolith; avoid microservices in MVP.
T005 | DevOps & Security | Week 1 | Create repository, branching, CI pipeline and code quality checks | PR build, lint and baseline unit tests run automatically | DevOps / Tech Lead | 2026-10-26 | 2026-11-02 | Not Started | 0% | Repository and cloud account access | High | 3 | Use approved company repositories and secret storage.
T006 | Data Foundation | Week 1 | Design canonical data model and tenant isolation | Reviewed ERD and initial schema for organizations, products, components, materials, suppliers and source lineage | Solution Architect / Backend Lead | 2026-10-27 | 2026-11-06 | Not Started | 0% | T001, T002 | Critical | 5 | Use relational columns for core/filterable fields; JSONB only for variable attributes.
T007 | Frontend | Week 1 | Create Angular application shell and navigation | App builds; module routes and basic product/import/issues/calculation navigation exist | Frontend Developer | 2026-10-26 | 2026-11-02 | Not Started | 0% | T004 | High | 4 | Use mock API responses until backend endpoints are ready.
T008 | Backend | Week 1 | Create FastAPI service, health endpoint and OpenAPI docs | Service starts in dev environment; health endpoint and API docs accessible | Backend Developer | 2026-10-26 | 2026-11-02 | Not Started | 0% | T004, T005 | High | 3 | Pin dependencies and add basic error handling.
T009 | Data Foundation | Week 2 | Build CSV/Excel upload and import staging | File upload, parse errors and import batch status are visible; original file retained securely | Backend / Data Engineer | 2026-11-02 | 2026-11-13 | Not Started | 0% | T002, T006, T008 | Critical | 6 | CSV first; Excel supported if representative client files require it.
T010 | Data Foundation | Week 2 | Implement field mapping, normalization and unit handling | Mapped records normalize material codes and weight units; mapping errors are reported | Backend / Data Engineer | 2026-11-02 | 2026-11-13 | Not Started | 0% | T006, T009, sample files | Critical | 5 | Never silently guess unknown units or material categories.
T011 | Backend & Data | Week 2 | Implement product, packaging and material CRUD APIs | Create/read/update/list endpoints pass API tests and enforce tenant access | Backend Developer | 2026-11-02 | 2026-11-13 | Not Started | 0% | T006, T008 | Critical | 6 | Add pagination and validation to list endpoints.
T012 | Frontend | Week 2 | Build product and packaging list/detail screens | Imported sample records visible; search/filter and detail view work against API | Frontend Developer | 2026-11-02 | 2026-11-13 | Not Started | 0% | T007, T009, T011 | High | 6 | Mock responses can be used until API integration is ready.
T013 | QA & Testing | Week 1-2 | Set up test data, unit tests and API integration test framework | Repeatable seeded dataset; tests run in CI; import and CRUD happy/error cases covered | QA / Backend Lead | 2026-10-29 | 2026-11-13 | Not Started | 0% | T005, sample files | High | 5 | Use anonymized/synthetic data until approved client data is available.
T014 | Data Quality | Week 3 | Implement required-field, type, range and unit validations | Invalid records create clear issues with rule ID, field, severity and evidence | Backend / Data Engineer | 2026-11-09 | 2026-11-20 | Not Started | 0% | T006, T009, T010 | Critical | 6 | Data quality status is separate from regulatory compliance status.
T015 | Data Quality | Week 3 | Build data issue queue and filters | Issues searchable by severity, status, owner and affected record | Frontend Developer | 2026-11-09 | 2026-11-20 | Not Started | 0% | T014 and API contract | High | 5 | Keep the UI workflow simple for first demo.
T016 | Workflow & Audit | Week 3-4 | Implement correction submission, review and approval | Correction can be submitted, approved/rejected, and revalidation reruns | Backend Developer | 2026-11-16 | 2026-11-27 | Not Started | 0% | T014, user roles defined | Critical | 7 | Preserve before/after values and actor/time in audit trail.
T017 | Workflow & Audit | Week 4 | Build correction form and issue detail UI | User can edit allowed fields, submit correction and see status/history | Frontend Developer | 2026-11-16 | 2026-11-27 | Not Started | 0% | T015, T016 API contract | High | 5 | Role-based approval must be enforced by backend.
T018 | EPR Rules & Calculation | Week 3 | Collect approved EPR rules, rates and reference examples | Target jurisdiction, reporting period, fee schedule and at least 3 expected-result cases signed off by SME/client | Product Owner / Regulatory SME | 2026-11-09 | 2026-11-20 | Not Started | 0% | Client compliance/regulatory owner | Critical | 4 | This is a blocker for validated calculation results.
T019 | EPR Rules & Calculation | Week 4 | Design versioned rule set and fee schedule tables | Draft/approved status, effective dates, version and immutable approved versions supported | Backend Lead / Regulatory SME | 2026-11-16 | 2026-11-27 | Not Started | 0% | T006, T018 | Critical | 5 | No universal formula assumed; model the selected jurisdiction's actual rules.
T020 | EPR Rules & Calculation | Week 5 | Implement EPR calculation engine for one jurisdiction | Component-level calculations use approved inputs/rules and return explainable fee breakdown | Backend Developer | 2026-11-23 | 2026-12-04 | Not Started | 0% | T010, T018, T019 | Critical | 8 | Missing required inputs must be flagged, not treated as zero.
T021 | EPR Rules & Calculation | Week 5-6 | Persist calculation runs, inputs, rule version and outputs | Run history can be reviewed and reproduced with same inputs and rule version | Backend Developer | 2026-11-23 | 2026-12-04 | Not Started | 0% | T019, T020 | High | 5 | Store run identifiers and versioned input references.
T022 | Frontend | Week 6 | Build EPR calculation page and fee breakdown | User selects jurisdiction/reporting period and views product/component fee details | Frontend Developer | 2026-11-30 | 2026-12-11 | Not Started | 0% | T020, T021 API contract | High | 6 | Show excluded products and reasons.
T023 | Integrations | Week 2-6 | Complete one-source integration feasibility spike | Documented proof of auth, data extraction, field mapping, errors and estimated next steps | Integration Engineer / Client IT | 2026-11-02 | 2026-12-04 | Not Started | 0% | T003; source access and vendor support | High | 8 | Do not block CSV-based MVP if credentials are delayed.
T024 | Analytics | Week 7 | Build cost hotspot summary by product/material | Ranked hotspots reconcile to calculation result totals | Backend + Frontend | 2026-12-07 | 2026-12-11 | Not Started | 0% | T020, T021 | Medium | 5 | Keep scope to simple rankings and charts.
T025 | Analytics | Week 7 | Build basic what-if scenario comparison | User changes one approved assumption and sees baseline vs scenario difference | Backend + Frontend | 2026-12-07 | 2026-12-16 | Not Started | 0% | T020, T021; SME validation | Medium | 6 | Label results as scenario estimates, not guaranteed savings.
T026 | QA & Testing | Week 4-7 | Run EPR reconciliation, edge case and regression tests | At least 3 approved reference cases pass; missing-data and boundary cases covered | QA / Regulatory SME | 2026-11-16 | 2026-12-16 | Not Started | 0% | T018, T020, client expected results | Critical | 7 | Record test evidence and any accepted deviations.
T027 | Security & SaaS | Week 5-7 | Implement and test role permissions and tenant isolation | Cross-tenant access tests fail safely; secrets not in code; access events logged | Backend / DevOps / QA | 2026-11-23 | 2026-12-16 | Not Started | 0% | Identity provider and tenant model decisions | Critical | 6 | Production readiness requires independent security review.
T028 | DevOps & Security | Week 6-7 | Deploy test/staging environment with backups and logging | Repeatable deployment, health checks, backups and operational logs verified | DevOps / Backend Lead | 2026-11-30 | 2026-12-16 | Not Started | 0% | Cloud account, security approvals | High | 5 | Use managed services where practical; Kubernetes not required for initial MVP.
T029 | QA & Testing | Week 8 | Run end-to-end UAT and regression cycle | Critical defects closed or explicitly accepted; UAT outcomes documented | QA / Product Owner | 2026-12-14 | 2026-12-18 | Not Started | 0% | T022, T024, T026, T027, T028 | Critical | 5 | Test on staging with representative data.
T030 | Delivery & Governance | Day 0 onward | Weekly demo, decision log and risk/dependency review | Weekly demo held; decisions, blockers, owners and due dates updated | Solution Architect / Product Owner | 2026-10-26 | 2026-12-18 | Not Started | 0% | Team and client availability | High | 8 | Keep feedback loop active throughout development.
T031 | Delivery & Governance | Day 0 onward | Daily stand-up and blocker escalation | Owners update status; blockers have named owner and next action | Project Lead | 2026-10-26 | 2026-12-18 | Not Started | 0% | Team cadence agreed | Medium | 8 | Keep stand-up short and action-oriented.
T032 | Future Modules | Post-MVP | Define PPWR, DPP and costing module backlog | Prioritized backlog, shared data reuse and regulatory dependencies documented | Product Owner / Solution Architect | 2026-12-14 | 2026-12-18 | Not Started | 0% | MVP feedback and client priorities | Low | 3 | Not included in 8-week EPR PoV delivery.

## Gantt
8-WEEK GANTT ¦ AUTO-UPDATED FROM TASKS
Bars are formula-driven from Tasks start/end dates. Change task dates on Tasks sheet to update. Weeks are shown from the project baseline start date.
Task ID | Workstream | Task | Owner | Start | Finish | Status | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8

## Weekly Plan
WEEKLY PLAN & EXIT CRITERIA
Use this as sprint planning agenda. Deliverables are proposed targets; confirm with team capacity and client readiness.
Week | Dates (baseline) | Primary outcome | Backend / Data | Frontend | QA / Testing | Client / Product input | Exit / Demo criteria
Day 0 | 26-Oct-2026 | Kick-off and remove unknowns | Repo/API skeleton; data model discovery | Agree UI shell and API contracts | Define test strategy and seeded data | Request samples, rulebook, API docs, source access | Owners, scope, risks and client requests tracked
Week 1 | 26-Oct–01-Nov | Architecture + working skeleton | FastAPI, Postgres schema draft | Angular shell/navigation | CI checks, unit-test scaffold | Confirm target jurisdiction and data owner | App builds; API health check; schema/API review
Week 2 | 02-Nov–08-Nov | First vertical slice in progress | Import staging, CRUD APIs, mapping | Product/packaging list and detail | Import/CRUD happy and failure cases | Provide sample files and field meanings | Demonstrate CSV → DB → API → UI
Week 3 | 09-Nov–15-Nov | Data quality and EPR rule discovery | Validation rules, issue API, rule data model | Issue queue, filters | Validation tests and issue test fixtures | Approve EPR jurisdiction and expected cases | Issues generated for known invalid rows
Week 4 | 16-Nov–22-Nov | Correction workflow | Correction/approval APIs, audit history | Correction form/detail | Workflow integration tests | SME clarifies exemptions and special cases | Correction → approval → revalidation demonstrated
Week 5 | 23-Nov–29-Nov | EPR engine implementation | Rule versioning and calculation core | Calculation page wire-up | Unit tests and first reconciliation | Approve rate schedule and 3+ reference cases | Calculation output explainable against approved rule version
Week 6 | 30-Nov–06-Dec | End-to-end EPR results | Persist runs/results; integration spike findings | Fee breakdown and run history | Reconciliation and edge cases | Client IT helps prove one source connector if possible | EPR flow works on representative sample
Week 7 | 07-Dec–13-Dec | Analytics and hardening | Hotspot aggregates/scenario endpoint | Dashboard and scenario compare | Regression, tenant/permission tests | Review results and prioritize fixes | Totals reconcile; scenario assumptions visible
Week 8 | 14-Dec–20-Dec | UAT and pilot decision | Bug fixes and deployment support | UX polish and demo | Full regression/UAT evidence | Stakeholder sign-off and next-phase priorities | Demo, known limitations, go/no-go and backlog

## Data & Integrations
CLIENT DATA & INTEGRATION TRACKER
Track what has been requested, received, validated and connected. Integration dates are estimates until client access is confirmed.
ID | Source / Dataset | Required fields / scope | Format / method | Client owner | Requested date | Received / access date | Status | Validation / next action | Risk / dependency
D001 | Product master | SKU, product name, category, brand/owner, source ID | CSV/Excel or API |  | 2026-10-26 |  | Requested | Check identifiers and duplicates | Client data owner
D002 | Packaging/BOM | Component ID, parent SKU, packaging level, material, component weight/unit | CSV/Excel or API |  | 2026-10-26 |  | Requested | Confirm component-to-product relationship and units | Data completeness
D003 | Sales / volumes | SKU, market/jurisdiction, reporting period, units sold | CSV/Excel or warehouse query |  | 2026-10-26 |  | Requested | Confirm period and units; no assumptions about market | Needed for fee calculations
D004 | Material taxonomy | Material codes, categories, subcategories, recyclability fields if applicable | CSV/Excel |  | 2026-10-26 |  | Requested | Map source values to canonical vocabulary | Unknown categories
D005 | EPR rulebook / fee rates | Official fee table, effective dates, adjustments, exemptions and scheme rules | Approved document/spreadsheet |  | 2026-10-26 |  | Requested | Regulatory SME/client signs off interpretation | Critical calculation dependency
D006 | Reference calculation cases | At least 3 representative products with expected fee breakdown and totals | Spreadsheet / approved examples |  | 2026-10-26 |  | Requested | Turn into automated regression tests | Critical acceptance gate
D007 | ERP integration | Product/BOM endpoints, auth, sandbox, pagination, rate limits, API version | API documentation + sandbox |  | 2026-10-26 |  | To Verify | Prove read-only access and field mapping | Vendor/client IT availability
D008 | PLM / Trace One | Product specifications, packaging attributes, API/export options | API docs / export |  | 2026-10-26 |  | To Verify | Verify product/API access and data scope | Access and license
D009 | Snowflake / warehouse | Relevant tables/views, service account, network access, query permissions | Read-only query / export |  | 2026-10-26 |  | To Verify | Confirm warehouse ownership and refresh cadence | Security/network approval
D010 | Identity provider | OIDC metadata, client registration, roles/claims | OIDC configuration |  | 2026-10-26 |  | To Verify | Use company-approved identity provider | Security team

## Risks & Decisions
RISKS, ASSUMPTIONS & DECISIONS
Update status and owners during weekly governance. Open risks should have a next action and due date.
ID | Type | Risk / decision | Impact | Mitigation / next action | Owner | Due date | Status | Decision / evidence
R001 | Risk | Client ERP/PLM API access or docs arrive late | Live integration cannot be completed on planned timeline | Use CSV/mock API while client IT confirms access; scope one connector only | Solution Architect / Client IT | 2026-11-06 | Open
R002 | Risk | No approved jurisdiction/rule schedule | EPR calculation cannot be validated | Obtain SME-approved fee schedule and reference cases before engine sign-off | Product Owner / Regulatory SME | 2026-11-20 | Open
R003 | Risk | Sample data incomplete or inconsistent | Import and quality workflow scope expands | Profile data in Week 1; agree a representative demo subset | Data Engineer / Client Data Owner | 2026-11-06 | Open
R004 | Risk | Team capacity less than assumed | 8-week target may slip | Assign named owners; reduce scope to one jurisdiction and no write-back | Project Lead | 2026-10-30 | Open
R005 | Risk | Cross-tenant data leakage | Severe security incident | Implement tenant checks at API/DB layer and test negative access paths | Backend Lead / QA | 2026-12-11 | Open
R006 | Assumption | CSV/Excel import is acceptable for MVP | Can start development without source APIs | Confirm with client in Day 0 kick-off | Product Owner | 2026-10-27 | Open
R007 | Decision | Select first EPR jurisdiction | Defines first rule model and tests | Record selected country/scheme and reporting year here | Client Product Owner / SME | 2026-10-30 | Pending
R008 | Decision | Choose tenant isolation pattern | Affects schema and authorization | Recommend organization_id + enforced row-level security for initial shared DB; validate with security review | Solution Architect | 2026-11-06 | Pending
R009 | Decision | Confirm hosting/cloud and identity provider | Affects deployment and authentication setup | Prefer client's existing cloud/identity where feasible; otherwise compare cost/security | DevOps / Client IT | 2026-11-06 | Pending
R010 | Assumption | No source-system write-back in initial MVP | Avoids source-system mutation and permissions complexity | Store approved corrections in Monkspaces; consider write-back in a later phase | Product Owner / Client IT | 2026-10-30 | Open

## Testing
TEST PLAN & DEFECT TRACKER
Start testing from Day 0. Add cases as the schema, validation rules and EPR rules become known.
Test ID | Area | Scenario | Expected result | Type | Priority | Owner | Status | Actual result / evidence | Defect ID
TC001 | Import | Upload valid product/packaging CSV | Records staged and imported; row counts visible | Integration | Critical |  | Not Started
TC002 | Import | Upload file with missing required column | Import rejected with actionable error; no silent partial import | Negative | High |  | Not Started
TC003 | Normalization | Weight values in g and kg | Normalized value is correct and original unit/source preserved | Unit | Critical |  | Not Started
TC004 | Data quality | Missing packaging weight | Data issue created with field, severity and affected record | Integration | Critical |  | Not Started
TC005 | Workflow | Submit correction then approve | New value applied; before/after and approver recorded; validation reruns | Integration | Critical |  | Not Started
TC006 | Workflow | Unauthorized user tries to approve correction | API denies action and records appropriate security event | Security | Critical |  | Not Started
TC007 | Tenant security | Tenant A requests Tenant B product ID | Access denied or non-disclosing not-found response | Security | Critical |  | Not Started
TC008 | EPR | Approved reference case 1 | Calculated total and line items match SME-approved expected result | Reconciliation | Critical |  | Not Started
TC009 | EPR | Approved reference case 2 | Calculated total and line items match SME-approved expected result | Reconciliation | Critical |  | Not Started
TC010 | EPR | Approved reference case 3 | Calculated total and line items match SME-approved expected result | Reconciliation | Critical |  | Not Started
TC011 | EPR | Required input missing | Record excluded/flagged with reason; not silently assigned zero fee | Negative | Critical |  | Not Started
TC012 | EPR | Repeat calculation with same input and rule version | Same output is reproducible and linked to same rule version | Regression | High |  | Not Started
TC013 | Analytics | Hotspot aggregation | Sum of grouped values reconciles to selected calculation total | Integration | High |  | Not Started
TC014 | Scenario | Change one scenario assumption | Baseline remains unchanged; scenario output shows delta and assumptions | Regression | Medium |  | Not Started
TC015 | Deployment | Deploy to staging and verify health/backup/logs | App is reachable; secrets absent from repo; backup/restore plan documented | Operational | High |  | Not Started

## Tech Stack
RECOMMENDED TECH STACK & ARCHITECTURE DECISIONS
Proposed baseline, not a vendor commitment. Confirm with Monkspaces standards, client security and hosting constraints.
Layer | Recommendation | Purpose | MVP decision / guidance | Status | Owner / notes
Frontend | Angular + TypeScript | Enterprise UI for product data, issue workflow, EPR results and dashboards | Use existing team expertise; define API contracts early | Proposed | Frontend Lead
Backend API | Python + FastAPI | REST APIs, validation and calculation logic; OpenAPI contracts | Modular monolith; separate modules in code, not separate microservices initially | Proposed | Backend Lead
Database | PostgreSQL | Relational canonical product/packaging data, workflow, rule versions and calculation history | Keep filterable/joinable fields relational; use JSONB only for truly variable attributes | Proposed | Solution Architect
File/evidence storage | S3-compatible object storage or Azure Blob | Store source files, evidence and generated exports | Use private buckets, encryption and retention controls | To Confirm | DevOps / Security
Identity | OIDC/OAuth2 using approved provider | Authentication and role claims | Prefer existing company/client identity where feasible; never implement custom password handling for MVP | To Confirm | Security / Client IT
Tenant isolation | organization_id + enforced DB/API access controls | Keep each customer's records isolated | Review PostgreSQL row-level security and negative cross-tenant tests | Design decision needed | Solution Architect
Data ingestion | CSV/Excel first; then one read-only API connector | Unblock data model while source APIs are assessed | Do not promise bidirectional sync until source capabilities and permissions are verified | Proposed | Integration Lead
Testing | pytest + API integration tests; Angular unit/E2E framework | Catch regressions and validate calculations | Tests run in CI; EPR reference cases require SME-approved expected values | Proposed | QA Lead
CI/CD | GitHub Actions or Azure DevOps | Build, lint, test and deploy repeatably | Use whichever is approved by company | To Confirm | DevOps
Runtime/deployment | Docker + managed application hosting | Consistent dev/test/staging environments | Kubernetes is not required for first MVP; choose managed services after cloud/security review | To Confirm | DevOps
Observability | Structured logs, health checks, cloud metrics | Diagnose failed imports, API errors and calculation runs | Do not log secrets or unnecessary client data | Proposed | Backend / DevOps
Regulatory logic | Versioned jurisdiction-specific rule sets | Reproducible fee calculations and effective dates | SME approval and regression cases are mandatory; no universal EPR formula assumed | Required | Product Owner / Regulatory SME